## Test Plan
Test plan for lazz pharma .pdf

## TestScenarios
Project Name | Lazz Pharma
Reference Document | FRS
Created By | Rokaiya Zaman Suthi
Creation Date | 20-08-2023
Approval Date | 22-08-2023
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the working of the "Login" functionality. | P0 | 19
TS_002 |  | Validate the "Signup" functionality | p0 | 17
TS-003 |  | Validate the "My profile" functionality | p2 | 27
TS_004 |  | Validate the "Homepage" functionality | p1 | 21
TS_006 |  | Validate the "category" functionality | P1 | 14
TS_007 |  | Validate the "Payment" functionality | p0 | 24

## TestCase
Product Name |  |  | TC Start Date | 2025-02-28 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 2025-03-01 | TC Execution End Date | - - |  |  |  |  | PASS | 117
Epic |  |  | Test Case Developed By | Rokaiya Zaman Suthi | Browser (tested) | Yes |  |  |  |  | FAIL | 3
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 123
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  |  | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Startech' 3. Go to the website. |  |  | Passed
2 |  |  | Signup | Verify user can sign up with valid details | Account is created successfully | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Signup" link |  |  | Passed
3 |  |  |  | Verify first name and last name fields are required | "This field is required" | Found not as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Out of Scope
4 |  |  |  | Verify email field accepts only valid format | "Enter a valid email" | Found not as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Out of Scope
5 |  |  |  | Verify phone number accepts only numeric values | "Enter a valid phone number | Found not as per expectation. | Aaa0172345 | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link | Screenshort |  | Failed
6 |  |  |  | Verify password field meets security criteria | "Password must be at least 8 characters" | Found not as per expectation. | 12345 | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link | Screenshort |  | Failed
7 |  |  |  | Verify OTP validation | "Invalid OTP" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
8 |  |  |  | Check duplicate email registration | "Email already exists" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
9 |  |  |  | Verify terms & conditions checkbox validation | "You must agree to the terms" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
10 |  |  |  | Verify password confirmation matches password | "Passwords do not match" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
11 |  |  |  | Check strong password requirement | "Password must contain letters and numbers" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
12 |  |  |  | Check form submission without entering any details | displayed for all fields | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
13 |  |  |  | Verify mobile number length limit | "Invalid phone number" | Found not as per expectation. | 1755 | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link | Screenshort |  | Failed
14 |  |  |  | Check existing phone number validation | Phone number already in use" | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
15 |  |  |  | Verify user receives a confirmation email | Email received with verification link | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
16 |  |  |  | Verify sign-up process on mobile devices | Form works properly on mobile | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
17 |  |  |  | Verify session persistence after sign-up | User remains logged in | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Passed
18 |  |  |  | Verify incorrect email format handling | Error should appear | Found not as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link |  |  | Out of Scope
19
20 |  |  | Log in | Verify user can successfully log in | User should be logged in | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
21 |  |  |  | Verify login with incorrect password | Error should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
22 |  |  |  | Checking login with unregistered phone number | Error should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
23 |  |  |  | Verify session handling post-login | User should remain logged in | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
24 |  |  |  | Verify password field security | Should be masked | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
25 |  |  |  | Verify multiple login attempts lockout | Account should be locked | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
26 |  |  |  | Verify login on multiple devices | Second session should log out first | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
27 |  |  |  | Verify remember me functionality | User should remain logged in | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
28 |  |  |  | Verify login with case-sensitive password | Password should be case-sensitive | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
29 |  |  |  | Verify login page responsiveness | Should be responsive | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
30 |  |  |  | Checking login via social media | Should log in successfully | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
31 |  |  |  | Verify error messages for empty login fields | Errors should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
32 |  |  |  | Verify logout functionality | User should be logged out | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
33 |  |  |  | Checking if error messages are user-friendly | Message should be clear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
34 |  |  |  | Verify login fails after multiple failed attempts | Account should be locked | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
35 |  |  |  | Verify session expiration | Session should expire | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
36 |  |  |  | Checking "Show Password" toggle | Should reveal password | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
37 |  |  |  | Checking error messages after failed login | Errors should be descriptive | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
38 |  |  |  | Verify case sensitivity in login credentials | Should be case-sensitive | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Login" link |  |  | Passed
39
40 |  |  | My Profile | Verify user can view order history | Order history should be displayed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
41 |  |  |  | Verify order status is updated correctly | Status should be "Confirmed", "Processing", etc. | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
42 |  |  |  | Verify prescription upload functionality | File should upload successfully | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
43 |  |  |  | Verify order saving with prescription | Order should be saved successfully | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
44 |  |  |  | Verify request history is displayed correctly | Previous requests should be listed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
45 |  |  |  | Verify profile editing | Changes should be updated | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
46 |  |  |  | Verify complaint submission | Complaint should be submitted | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
47 |  |  |  | Verify complaint selection | List of complaints should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
48 |  |  |  | Verify payment history is displayed | Payment details should be visible | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
49 |  |  |  | Verify logout functionality | User should be logged out | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
50 |  |  |  | Check order history filtering | Orders should be filtered accordingly | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
51 |  |  |  | Verify "All" orders option | All orders should be displayed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
52 |  |  |  | Verify prescription file format validation | Error message should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
53 |  |  |  | Verify note saving in prescription order | Note should be saved | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
54 |  |  |  | Verify order cancellation | Order should be canceled | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
55 |  |  |  | Verify invalid prescription upload | Error should be displayed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
56 |  |  |  | Verify prescription deletion | Prescription should be removed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
57 |  |  |  | Check email validation in profile edit | Error message should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
58 |  |  |  | Verify phone number format in profile edit | Error message should appear | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
59 |  |  |  | Check special characters in complaint description | System should allow/disallow based on policy | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
60 |  |  |  | Verify user can request order from history | Order should be added to cart | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
61 |  |  |  | Verify search within order history | Relevant orders should be displayed | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
62 |  |  |  | Check duplicate complaint submission | System should prevent duplicate submission | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
63 |  |  |  | Verify complaint status update | Complaint status should update | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
64 |  |  |  | Verify saved profile updates after page refresh | Changes should persist | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
65 |  |  |  | Verify logout during an order process | User should be logged out, order should not be lost | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
66 |  |  |  | Verify order details page | Order details should be visible | Found as per expectation. | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the profile on the right corner |  |  | Passed
67
68 |  |  | Home Page | Verify home page loads correctly | Home page should load with all elements visible | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
69 |  |  |  | Checking responsiveness of the home page | Page should adjust properly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
70 |  |  |  | Verify search bar functionality | Relevant results should appear | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
71 |  |  |  | Checking search with incorrect input | No results or "No products found" message | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
72 |  |  |  | Verify homepage banner images load | All banners should display correctly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking homepage navigation links | Should navigate to correct pages | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify special offers are displayed | Special offers should be listed | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking order request functionality | Should redirect to order request form | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify branch locations are displayed correctly | Should show correct addresses | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking review section visibility | User reviews should be visible | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify contact information is correct | Contact details should be accurate | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify homepage loads within acceptable time | Should load within 3 seconds | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking homepage search with special characters | Should handle input properly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking homepage product categories | All categories should be listed | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify homepage auto-scroll for banners | Should auto-scroll banners every few seconds | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking alignment of homepage sections | Sections should be well aligned | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify promotional banners are clickable | Should redirect to relevant page | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify homepage icon visibility | Should be visible and functional | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify error handling for broken links | No 404 errors should appear | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Checking homepage zoom functionality | Should work without breaking layout | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  |  | Verify scrolling behavior | Should be smooth without lag | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the home icon |  |  | Passed
|  |  | category | Verify category section loads correctly | The page should display all categories without errors | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking the total number of categories displayed | All available categories should be listed | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify clicking a category displays relevant products | Only prescription medicine products should be shown | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking empty category handling | Should show a message like "No products available" | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify category filter functionality | Should display filtered products | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking category navigation | Should navigate to respective product lists | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify category sorting options | Products should be sorted correctly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking category pagination | Next page should load smoothly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify product count under each category | Should match actual product availability | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking mobile responsiveness of categories | Categories should be displayed properly | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking search within a category | Should return results only from that category | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify category images display correctly | All images should be visible and properly aligned | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Checking category performance speed | Should load within 3 seconds | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  |  | Verify broken links in categories | No broken links or 404 errors should appear | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Click on the category icon |  |  | Passed
|  |  | Payment | Verify payment page loads correctly | Payment page should load without errors | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking available payment methods | Should display Cash on Delivery, Card, and Online Payment options | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify card payment option selection | Should proceed to card details entry page | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking online payment gateway redirection | Should redirect to payment gateway | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify Cash on Delivery (COD) option | Should allow order placement without online payment | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking invalid card number entry | Should display an error message | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify expired card entry | Should reject payment | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify successful card payment | Payment should be processed successfully | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking failed transaction handling | Should show "Transaction Failed" message | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify coupon code application | Should apply discount | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking invalid coupon handling | Should display "Invalid Coupon" error | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify payment confirmation email | Confirmation email should be sent | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking order status update after payment | Should update to "Confirmed" | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify canceling payment | Should return to checkout without charge | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking auto-fill functionality for saved cards | Should auto-fill details securely | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify multiple payment attempts | Should not double charge | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking payment receipt generation | Should generate and download receipt | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify guest user payment process | Should allow payment without an account | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking session timeout handling | Should prompt to refresh session | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify incorrect OTP handling | Should reject transaction | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking successful OTP payment | Should approve payment | Found not as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify refund process | Refund should process successfully | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Checking error message clarity | Should show meaningful error messages | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
|  |  |  | Verify mobile responsiveness of payment page | Payment options should be accessible and functional | Found as per expectation | None | 1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "log in" link 4. Select product then add to bag then order now |  |  | Passed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Lazz Pharma Limited
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Signup,Login,My Profile,Homepage,Category,Payment
Test Case Version | 1 |  |  |  |  | 117 | PASS
Written By | Rokaiya Zaman Suthi |  |  |  |  | 3 | FAIL
Executed By | Rokaiya Zaman Suthi |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 3 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 117 | 3 | 0 | 0 | 123
Grand Total | 117 | 3 | 0 | 3 | 123
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Verify phone number accepts only numeric values
Reproducing Steps:
1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link
Env: Production
Module: Signup
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort
Responsible QA: Rokaiya Zaman Suthi
Bug Reporting
# SL 02
Issue: Verify password field meets security criteria
Reproducing Steps:
1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link
Env: Production
Module: signup
Priority: High ¦ Medium ¦ Low
Screenshort
Responsible QA: Rokaiya Zaman Suthi
Bug Reporting
# SL 03
Issue:Verify mobile number length limit
Reproducing Steps:
1. Goto the URL https://www.lazzpharma.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign Up" link
Env: Production
Module: Signup
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort
Responsible QA: Rokaiya Zaman Suthi

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (123/123)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (117/123)*100 = 95%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (3/123)*100 = 2%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/123)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A